SCRUM MANGEMENT

GROUP 6  
תאריך הגשה :  16/05/2026

| Name | Email | ID |
| --- | --- | --- |
| Lamis Odtalla | Lamis.Odtalla@e.braude.ac.il | 212760532 |
| Fares Ali Naser | Fares.ali.naser@e.braude.ac.il | 325479020 |
| Hasan Mughrabi | Hasan.mughrabi@e.braude.ac.il | 322968082 |
| Hadi Shofania | Hadi.Shofania@e.braude.ac.il | 212152979 |
| Tali Hamoud | Tali.hamoud@e.braude.ac.il | 213857949 |

Project Management & Roles

This document explains how our team GROUP 6 uses the Scrum approach to manage the development of the Go Nature system. Go Nature is a distributed system designed to manage park visits, traveler services, and data processing for the "Parks and Recreation" department.

Roles & Responsibilities

Product Owner: Hadi Shofania

Responsible for the Go Nature vision and requirements:

- Prioritizing the Product Backlog based on the system's core needs (e.g., booking visits, group reservations, and member management).

- Working with stakeholders to define park capacity quotas and pricing models.

- Verifying that features like the simulation of SMS/Email notifications meet the requirements.

Scrum Master: Fares Ali Naser

Responsible for the Scrum process and team efficiency:

- Leading Scrum meetings and ensuring the team follows Agile principles throughout the Go Nature development phases.

- Removing blockers to ensure the successful delivery of the Full-stack architecture (Client-Server).

- Ensuring the team stays focused on the Sprint goals, such as implementing the "Traveler Services" or "Access Control" modules.

# Sprint backlog

# Week 1

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Project Setup & Scrum Initialization | All | 2.00 hours | ✅ Done |
| Requirements Analysis | Tali , Lamis | 2 hours | ✅ Done |
| Brainstorm system actors & roles | Fares , Hadi , Hasan | 2.00 hours | ✅ Done |
| Sprint Planning | Lamis,Fares,Hadi | 1.00 hour | ✅ Done |

# Week 2

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Use Case Diagram | Fares , Hadi , Hasan | 5.00 hours | ✅ Done |
| Acceptance Test Design | Hadi, Hasan , Lamis, Tali | 3.00 hours | ✅ Done |
| Sprint Review and Submission assignment 1 | All | 2.00 hours | ✅ Done |

# Week 3

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Assignment 2 setup | All | 2.00 hours | ✅ Done |
| Build the Park Reservation diagram | Lamis ,Hadi | 3.00 hours | ✅ Done |
| Build the Visit Report activity diagram | Fares,Hasan,Tali | 3.00 hours | ✅ Done |

# Week 4

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Double-check that all use cases are covered | All | 1.00 hours | ✅ Done |
| Fix and refine Use Case Diagram based on team feedback | Hadi,Fares,Hasan | 2.00 hours | ✅ Done |
| Polish flow of events texts to match diagram accurately | Tali, Lamis | 1.00 hours | ✅ Done |
| Confirm all ZIP files meet instructions and sumbiting assinment on Moodle and GitHub | Hadi | 0.50 hours | ✅ Done |

# Week 5

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Software Structure Description | Hadi , Fares, Hasan | 6.00 hoors | ✅ Done |
| integrate OCSF | Tali ,Lamis , Fares | 6.00hours | ✅ Done |
| Apply design pattern | all | 6.00 hours | ✅ Done |

# Week 6

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Sequence Diagram cancel reservation | Lamis, Hadi , Fares | 3.00 hours | ✅ Done |
| Sequence Diagram Park Entry and payment Control | Hadi , Hasan ,Tali | 6.00 hours | ✅ Done |
| Sequence Diagram Park Visit Reservation and Visit Report | Tali , Fares | 5.00 hour | ✅ Done |
| Refining Class Diagram with ECB Pattern | Lamis ,Fares | 8 hour | ✅ Done |
| Create the Package Diagram in Visual Paradigm with all dependencies | Hasan , Tali | 2.00 hours | ✅ Done |

# Week 7

| Task | Owner(s) | Duration | Status |
| --- | --- | --- | --- |
| Database Setup | Hadi , Fares ,Hasan | 2.5 hours | ✅ Done |
| Building Server Prototype | Lamis ,Tali , Fares | 10.00 hours | ✅ Done |
| Building Client Prototype | Hadi , Fares ,Hasan | 12.00 hours | ✅ Done |
| Final Testing & Documentation | All | 8.00 hours | ✅ Done |
| Submission assignment 2 | All | 1.00 hours | ✅ Done |

GoNature – Group 6  |  WBS Project Schedule

| ID | Task Name | Description | Start | End | Dependencies | Team Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| WEEK 1 ¦ Sprint 1 – Assignment 1 ¦ 29/03/26 – 05/04/26 |  |  |  |  |  |  |
| 1.1 | Project Setup & Scrum Init | Create Eclipse/Java env, assign Scrum Master Product Owner, open GitHub repo, create initial Product Backlog | Sun 29/03 | Sun 29/03 | — | All |
| 1.2 | Requirements Analysis | Gather and document functional (FR) and non-functional (NFR) requirements; identify system actors; produce SRS draft. | Tue 31/03 | Wed 01/04 | 1.1 | Tali, Lamis |
| 1.3 | Brainstorm Actors & Use Cases | Identify all actors (Traveler, Guide, Park Worker, Park Manager, Dept. Manager, Service Rep.). Draft initial use-case list for GoNature. | Wed 01/04 | Thu 02/04 | 1.2 | Hasan, Fares, Hadi |
| 1.4 | Sprint Planning | Create detailed task list for Sprint 1; assign owners, estimates and deadlines. Document sprint backlog. | Thu 02/04 | Thu 02/04 | 1.1 | Lamis, Fares, Hadi |
| WEEK 2 ¦ Sprint 1 Continued ¦ 06/04/26 – 12/04/26 |  |  |  |  |  |  |
| 2.1 | Use Case Diagram | Identify all use cases draw complete diagram, write Flow of Events for each main use case | Sun 06/04 | Tue 08/04 | 1.3 | Hasan, Fares, Hadi |
| 2.2 | Acceptance Test Design | Define acceptance tests for: Visit Booking. park entry, Visit Report generation. Fill Excel table: TEST ID, DESCRIPTION, PRECONDITION, STEPS, EXPECTED RESULT, COMMENTS. | Mon 07/04 | Tue 08/04 | 2.1 | Hadi, Hasan, Lamis, Tali |
| 2.3 | Sprint Review & Submission – Assignment 1 | Review all deliverables, fix issues, package ZIP (VP file + Excel),upload to Moodle + GitHub. Deadline: 12/04/26 | Wed 08/04 | Sat 12/04 | 2.1, 2.2 | All |
| WEEK 3 ¦ Sprint 2 – Assignment 2 Start ¦ 13/04/26 – 19/04/26 |  |  |  |  |  |  |
| 3.1 | Assignment 2 Setup | Read Assignment 2 , Understanding assignment 2 and assign roles | Sun 13/04 | Mon 14/04 | 2.3 | All |
| 3.2 | Activity Diagram – Visit Booking and Park Entry | Model full booking flow (booking → waitlist → reminder → confirm/cancel → park entry → payment) using Swim-Lane Activity diagram | Mon 14/04 | Wed 16/04 | 3.1 | Lamis, Hadi |
| 3.3 | Activity Diagram – Visit Report Creation | Model report generation flow (park manager monthly report + dept. manager reports incl. graphical display) using Swim-Lane Activity diagram. | Mon 14/04 | Wed 16/04 | 3.1 | Fares, Hasan, Tali |
| WEEK 4 ¦ Sprint 2 Continued ¦ 20/04/26 – 26/04/26 |  |  |  |  |  |  |
| 4.1 | Class Diagram – ECB + OCSF + Design Pattern | Full UML Class diagram: ECB pattern (Entity/Control/Boundary), OCSF classes, JDBC and JavaFX packages, at least 1 Design Pattern . Add annotation comment with pattern location. | Sun 20/04 | Tue 22/04 | 3.2, 3.3 | Hadi, Fares, Hasan |
| 4.2 | Class Diagram – Methods and Refinement | Add specific methods to all classes; multiplicities, visibility modifiers, associations, aggregations, compositions. Team review. | Wed 23/04 | Thu 24/04 | 4.1 | Lamis, Fares |
| 4.3 | Package Diagram | Create Package Diagram showing packages (client, server, entities, common) and dependencies. Ensure future Web extensibility. | Thu 24/04 | Fri 25/04 | 4.1 | Hasan, Tali |
| WEEK 5 ¦ Sprint 3 – Sequence Diagrams & Prototype Design ¦ 27/04/26 – 03/05/26 |  |  |  |  |  |  |
| 5.1 | Sequence Diagram – Visit Booking (Cancel, Entry, Payment) | Model: Traveler/GUI, BookingController, WaitlistController, ParkDB, NotificationService, EntryController, PricingController. Cover booking, capacity check, waitlist, reminder, confirm/auto-cancel, entry, bill. | Sun 27/04 | Mon 28/04 | 4.2 | Tali, Fares |
| 5.2 | Sequence Diagram – Visit Reports | Model: Park Manager selects params → ReportController queries DB → builds stats → graphical display. Cover visit report and cancellation report. | Sun 27/04 | Mon 28/04 | 4.2 | Hadi, Hasan |
| 5.3 | Prototype DB Setup | Create MySQL DB; create table 'Order' (order_number PK, order_date, number_of_visitors, confirmation_code, subscriber_id FK, date_of_placing_order); insert sample data. | Tue 29/04 | Tue 29/04 | 4.1 | Hadi, Fares, Hasan |
| 5.4 | Sequence Diagrams Review & Consistency Check | Verify diagrams are consistent with Activity and Class diagrams. Check English naming. Export all diagrams from VP. | Tue 29/04 | Wed 30/04 | 5.1, 5.2 | All |
| WEEK 6 ¦ Sprint 4 – Prototype Build ¦ 04/05/26 – 10/05/26 |  |  |  |  |  |  |
| 6.1 | Server Prototype – DB Connection and Read/Write | Implement AbstractServer; connect MySQL via JDBC; handleMessageFromClient(); SELECT * from Order; UPDATE order_date & number_of_visitors. Show client IP/hostname + connection status in Server GUI. | Sun 04/05 | Mon 05/05 | 5.3 | Lamis, Tali, Fares |
| 6.2 | Client Prototype – GUI Read/Write and Multi-Client | Implement AbstractClient; build JavaFX GUI showing Order fields; add Update button for order_date & number_of_visitors; test with 2 simultaneous clients; build client JAR. | Mon 05/05 | Tue 06/05 | 6.1 | Hadi, Fares, Hasan |
| 6.3 | Prototype End-to-End Testing and Bug Fixes | Full scenario: start server → connect 2 clients → read from DB → update fields → verify directly in MySQL. Fix all bugs. | Wed 07/05 | Thu 08/05 | 6.1, 6.2 | All |
| WEEK 7 ¦ Sprint 5 – Final Review & Submission 2 ¦ 11/05/26 – 17/05/26 |  |  |  |  |  |  |
| 7.1 | UML Diagrams Final Review | Review all diagrams (Activity, Class, Sequence, Package) for consistency, completeness and English naming. Apply last corrections in VP. | Sun 11/05 | Mon 12/05 | 6.3 | Hadi, Fares, Lamis |
| 7.2 | Sprint Backlog Doc Finalization | Finalize SprintBacklog_G6 Word doc: all 5 sprints, roles, hours per task, responsible member for each task. | Mon 12/05 | Tue 13/05 | 7.1 | Tali, Lamis |
| 7.3 | ZIP Packaging and Final QA | Package Assignment 2 ZIP: VP file, SprintBacklog DOC, Server.jar, Client.jar (flat structure, no sub-folders). Verify all file names match requirements. | Wed 14/05 | Thu 15/05 | 7.2 | All |
| 7.4 | Submission – Assignment 2 | Upload ZIP to Moodle + GitHub link in comments. Verify successful upload (no draft status). Deadline: 17/05/26 08:30. | Thu 15/05 | Sat 17/05 | 7.3 | All |